## Glossary
Description | Purpose
Sr.No | Sequencial number
Module | Module for which the test case belongs.
Area/Agenda Topic | To capture the topic to which the test case belongs.
Business Scenario/Cases | Test Case description that is required to be performed in oracle.
Priority | The column helps to prioritise the test case. The test case can be bifurcated into Critical, High, Medium and Low.
Owner | To provide details of person owning the test case.

## ERP PPM Business Scenarios
Sr.No | Module | Requirement Name/Agenda Topic | Business Scenarios | Priority | Owner
1 | Project Financials | Project Foundation | Create a new OPEX Project from template or existing project
2 | Project Financials | Project Foundation | Create a new Research Project from template or existing project
3 | Project Financials | Project Foundation | Create a new Capital Project from template or existing project
4 | Project Financials | Project Foundation | Create a project from RIS with necessary details such as Project Name and Number
5 | Project Financials | Project Foundation | Enter/update project detail i.e. Project Description, Project name, additional information, project date etc.
6 | Project Financials | Project Foundation | Assign the Organization/Department to which the Project belongs
7 | Project Financials | Project Foundation | Setup a timeline for a Project by entering Start Date and End Date
8 | Project Financials | Project Foundation | Add Project Classifications such as schemes, research topics, programme etc to classify a Project
9 | Project Financials | Project Foundation | Attach Documents, URLs or Text as support objects to review in a Project
10 | Project Financials | Project Foundation | Associate Team Members in a Project such as Project Manager, Principal Investigator, Finance Manager etc
11 | Project Financials | Project Foundation | Enter Transaction Controls to restrict the expenditure types (type of costs) to be charged on either at Project Level or Task Level, for example: capital project enabled with transaction controls restricting only capital expenditure types to be allowed to be charged
12 | Project Financials | Project Foundation | Edit currency details for Projects requiring a currency other than the default ledger currency
13 | Project Financials | Project Foundation | Define Asset details such as Asset name, Asset description, Asset Book, Depriciation account, as built date etc for the capital project
14 | Project Financials | Project Foundation | Enter Additional Information needed to be captured for reporting or accounting purposes
15 | Project Financials | Project Foundation | Add Tasks to the Work Breakdown Structure and give task number and task name to the same
16 | Project Financials | Project Foundation | Setup a timeline for the Tasks created by entering Planned Start Date and Planned End Date
17 | Project Financials | Project Foundation | Enter Task Description to describe the objective of the Task
18 | Project Financials | Project Foundation | Attach Documents or Notes specific to a task
19 | Project Financials | Project Foundation | Enable or disable task for Billing, eligible for charging or capitalization depending on the requirement of treating the Project costs
20 | Project Financials | Project Foundation | Change project status as per requirement. PPM allows send project status notification to approver i.e draft to submitted and once approved project status can be Active.
21 | Project Financials | Project Control | Creation of Funding budgets for Sponsored Projects and Cost budgets for OPEX or Capital Projects
22 | Project Financials | Project Control | Enabling Budgetary controls for the Project Budgets to track/control the spending on Project
23 | Project Financials | Project Control | Enter budgeted amounts either for each period or sum total budget amount on Resource level
24 | Project Financials | Project Control | Baseline the Budget by getting it approved
25 | Project Financials | Project Control | Amend details of the approve budget by editing period amounts
26 | Project Financials | Project Control | Create Forecast from the baselined budget to track Actual Cost, ETC (Estimation to Complete) and EAC (Estimation at Complete)
27 | Project Financials | Project Control | Capture progress to track the current status of projects and measure the amount of work remaining.
28 | Project Financials | Project Costing | Capture project-related costs from both Oracle Cloud and third-party applications (like Concerto) and then transfer them to Oracle Projects
29 | Project Financials | Project Costing | Create Miscellaneous cost transactions and charge it to Projects by entering details like Project Number, Task number, expenditure type (type of cost), costing organization (cost centre) and amount
30 | Project Financials | Project Costing | Create Non matched PO Invoices in Oracle Fusion AP with project details in it and transfer it to Oracle Fusion Projects. Project accountants import the invoices into Project Costing for costing, accounting, and analysis
31 | Project Financials | Project Costing | Raise Purchase Requisitions with Project details in it and transfer the cost to Projects. Project accountants import the requistions into Project Costing for costing, accounting, and analysis
32 | Project Financials | Project Costing | Manage time cards for employees and contingent workers by entering timesheets in Oracle Fusion Time & Labor with Project details in it. Project managers can review and approve the time card entries created for their projects. Project accountants import the time cards into Project Costing for costing, accounting, and analysis
33 | Project Financials | Project Costing | Capturing and summarizing commitments from outstanding purchase requisition or purchase order, payable invoice charged to a project, or received goods that aren't yet paid for
34 | Project Financials | Project Costing | Perform adjustments to the processed project costs and commitments after reviewing them in Oracle Fusion Project Costing
35 | Project Financials | Project Costing | Distributing Overhead Costs to Projects by performing a summation of overhead costs (burden costs) with raw costs to provide a true representation of costs.
36 | Project Financials | Project Costing | Allocating common costs from a source to target projects. Allocations are processed to distribute various types of costs to distinct sets of target projects and tasks.
37 | Project Financials | Project Costing | Capture and Collect construction-in-process (CIP) costs for capital assets created in Capital Projects
38 | Project Financials | Project Costing | Transfer the Asset created by the Capital Project to the Asset Book after capitalizing all the Project costs
1 | Grants Management | Grants Management | Receiving grants from sponsor where funds has been specified for a purpose like Research, Donations or Capital Asset building and creating Awards for the same in Grants Management
2 | Grants Management | Grants Management | Associating a Project to the Award to incur and track the costs against the same
3 | Grants Management | Grants Management | Adding Fund details such as the Sponsor name, amount received, duration etc
4 | Grants Management | Grants Management | Creating Award Budget to track and control the costs incurred against the Sponsored Projects
5 | Grants Management | Grants Management | Creation of a contract with the Sponsor to raise invoices
1 | Project Contract & Billing | Project Contract | Creating Research Contracts in Contract Management and associating them with the respective research projects
2 | Project Contract & Billing | Project Contract | Entering necessary details in the Contract created like the name of the party with whom the contract is entered with, contract amount, billing details etc
3 | Project Contract & Billing | Project Contract | Attaching documents related to contract for reviewing
4 | Project Contract & Billing | Project Billing | Creation of Invoices to be presented to the Contracted Party
5 | Project Contract & Billing | Project Billing | Creation of credit note against the invoices already issued
6 | Project Contract & Billing | Project Revenue | Recognition of revenue against Revenue Projects through automatic revenue recognition methods. Some of the automatic revenue recognition methods are Percentage Spent, Percentage completed etc
7 | Project Contract & Billing | Project Revenue | Recognition of revenue against Revenue Projects through manual creation of revenue events